SEARCH FOR PARTNERS

PROGRAMME “EUROPE FOR THE CITIZENS”;

CALL FOR PROPOSALS FOR PROJECTS TO BE SUBMITTED ON JUNE, 1ST 2012.

The following lines intend to present the main ideas of the project the Regional Ministry of Equality and Social Welfare of Junta de AndalucÍa is developing currently to submit under the call of proposals of the programme  Europe for  the Citizens. The drafting the project undergoes may modify slightly the general information described below. In case your organization is interested in participating in the project as a partner, do not hesitate to send your letter of intention or inquiry together with the document “proposal of partners” fulfilled to Mr Raúl Algarín to oficina.asuntos.europeos.assda@juntadeandalucia.es; raul.algarin@juntadeandalucia.es,  before 15 May 2012.

| NAME OF THE PROJECT | Volunteering in Movement (VIM) |
| --- | --- |
| DEADLINE FOR SUBMISSION | 1 June 2012 |
| PROJECT MANAGEMENT PERIOD | November 2012 – October 2013 (12 months) |
| BUDGET | It would depend on the number of partners and their location. It is expected to count on 5 regional partners. |
| CALL PRIORITY | Action 1. Measure 2.1. Citizens’ projects. This measure aims at exploring innovative methodologies and approaches to encourage citizens’ active participation at European level and to stimulate the dialogue between European citizens and European institutions. Under this measure a variety of projects of a transnational and cross-sectoral dimension, directly involving citizens will be supported. Priority is given to projects aimed at encouraging local level participation. |
| OBJECTIVES | O.1. (General objective) To analyse key questions that shape volunteering in our context. O.2. To identify traditional and new ways of social participation, establishing paths of coordination among the different initiatives. O.3. To analyse the answer of volunteers to contemporary technological and social contexts. O.3. To apply conclusions of the former analysis to the local level. O.4. To keep dialogue among the participating entities at European level in both the short and long term and disseminate the debates and initiatives of the project through the REVOS site. |
| TARGET GROUP | Public bodies involved in the management of volunteering; managers of volunteering in associations and NGO; volunteers and active participants in less organised environments, as it is the case of the movement “15-M” in Spain. |
| ACTIVITIES | A.1. Analysis of organisational structures supporting volunteering in each participating region, as well as their connection/ ramification with other national and European regions. The activity will be carried out through focus groups that will count on the participation of key agents/reporters/delegates identified previously. A.2. Analysis of the contemporary forms of volunteering by means of working groups and social research, including the volunteering linked to associations, the occasional volunteering, the spontaneous or shapeless volunteering (15-M, Violet Wave, Red Wave, Blue Wave, etc. In the case of Spain), citizens’ platforms and cross-border movements. A.3. Debates on third sector and volunteering about fundamental questions such as (a) democracy and EU; (b) consumerism and European citizenship; (c) borders and cooperation between social entrepreneurship and volunteering; (d) volunteering activity and independence from politics and economics; (e) impact of TICs on volunteering; (f) coordination of volunteering. A.4. Draft and submission of an analysis of the volunteering in Europe, containing different sets of recommendations on management addressed to the third sector, the volunteers themselves and Public Administrations. |
| POSSIBLE PARTNERSHIP | - Platforms of volunteers of other Member States - Public Administrations of candidate States (Entities from Western Balkans are welcome to join) - Volunteering organizations at local level inserted in broader networks (from Member States and candidate States) |
| PREVIOUS EXPERIENCE OF THE JUNTA DE ANDALUCIA | The Junta de Andalucía is the regional government of Andalusian, in Southern Spain. The Directorate General of Volunteering and the Directorate General of Social Services and Attention to Drug Dependence treasure a great experience on volunteering and keep a close contact with third sector organisations. Moreover, the Directorate General of Social Services counts on a very valuable experience in European projects in the last decade. From 2004 to 2006 it was Lead Partner to the INTERREG III-C REVOS project, whose web turned into a news site that was renewed recently in order to guarantee a more modern outlook and its interactivity with Internet social networks. |
| FURTHER INFORMATION ABOUT THE CALL FOR PROPOSALS | For further information on the programme: http://eacea.ec.europa.eu/citizenship/programme/documents/2011/programme_guide_en.pdf |